| April 11 – May 6 | Work groups complete project recommendations |
| --- | --- |
| May 7 | Work groups submit revised project |
| May 9 | Final Stakeholders Meeting |
| May 12 – May 23 | Consultants draft PEI Plan in consultation with work group leaders & H&SS |
| June 7 - 11 | H&SS final review and approval plan |
| June 13 | Beginning of 30 day public review comment period |
| June/July (TBD) | MHB reviews and approves plan |
| July 14 (Proposed) | MHB public hearing on plan |
| July 15 -18 | Consultants, H&SS review and respond to public comments |
| July 21 | Final plan submitted to DMH |